## Sheet1
Product Backlog sample for Social media application
ID | Title | Epic | User Story | Priority (MoSCoW) | Status | Acceptance Criteria | Functional Requirements | Non-Functional Requirements | Original Estimate | Actual Effort (In days)
1 | Owner Registration | User Management | As a vehicle owner, I want to be able to register my vehicle on the platform with legal documents. | MUST | In Progress | Owner can successfully upload required legal documents (RC, Insurance) during registration. | Securely upload and store vehicle legal documents. | Ensure data privacy and compliance with legal requirements. | 3 | 2
2 | Customer Login | User Management | As a customer, I want to be able to log in to the platform securely. | MUST | Completed | Customer can successfully log in using valid credentials. | Enable secure customer login using email/password or social login. | Implement robust security measures to protect user credentials. | 1 | 1
3 | Vehicle Search by Location | Vehicle Browsing | As a customer, I want to be able to search for vehicles based on location. | MUST | In Progress | Customer can search for vehicles by city/area and see available options. | Allow users to search for vehicles based on location. | Ensure accurate location-based search results. | 2 | 1
4 | Payment Processing | Payment | As a customer, I want to be able to make payments securely for my bookings. | MUST | To Do | Customer can successfully make a payment using a credit card or other payment method. | Integrate with a secure payment gateway (e.g., Stripe, PayPal). | Comply with PCI DSS standards for payment security. | 5 | TBD
5 | Vehicle Listing Management | Vehicle Management | As an owner, I want to be able to add, update, and delete my vehicle listings. | MUST | To Do | Owner can add new vehicles with all required details, update existing listings, and remove vehicles. | Provide an interface for vehicle owners to manage their vehicle listings. | Ensure vehicle listing information is accurate and up-to-date. | 4 | TBD
6 | Booking Management | Booking | As a customer, I want to be able to book a vehicle for a specific duration. | MUST | To Do | Customer can select a rental duration and book the vehicle for those dates. | Enable customers to select a rental duration and book the vehicle. | Ensure accurate booking management and availability tracking. | 3 | TBD
7 | Display Vehicle Details | Vehicle Browsing | As a customer, I want to see detailed information about a vehicle before booking. | MUST | Completed | Customer can view vehicle details, including images, features, and owner ratings. | Display detailed vehicle information, including images, features, and ratings. | Ensure vehicle details are comprehensive and accurate. | 2 | 2
8 | Vehicle Owner Legal Document Verification | User Management/ Compliance | As an admin, I need a way to verify the legal documents submitted by vehicle owners. | SHOULD | To Do | Admin can review uploaded documents and approve/reject vehicle listings based on verification. | Provide an admin interface for reviewing and verifying legal documents. | Ensure compliance with legal and regulatory requirements. | 5 | TBD
9 | Implement Notification Service | Communication | As a user, I want to receive notifications for booking confirmations and reminders. | SHOULD | To Do | Users receive email/SMS notifications for booking confirmations, cancellations, and rental reminders. | Implement a notification service to send email/SMS notifications. | Ensure timely and reliable notifications. | 3 | TBD